GridSensai Research Extraction Template

Section Title

Pain Points and Frustrations (Section 7)

Question

39. What is the most frustrating part of the grid interconnection process for data centers?

Extracted Answer

Multiple industry reports indicate that the most frustrating issue is the uncertainty and lack of transparency in interconnection timelines and upgrade costs. Developers often do not know early in the process whether major transmission upgrades will be required or how long studies will take. The absence of standardized large‑load processes across utilities further increases uncertainty for developers planning multi‑billion‑dollar facilities.

Source

GridLab (2025) Practical Guidance and Considerations for Large Load Interconnections

Brattle Group & Berkeley Lab (2025) Large Loads: Interconnection, Tariff Designs, and State Actions

NERC (2025) Characteristics and Risks of Emerging Large Loads

Evidence or Key Passage

• GridLab notes that utilities often lack a transparent or standardized process for large load interconnection, creating uncertainty around timelines and upgrade requirements.

• Brattle/Berkeley Lab report that many jurisdictions do not have publicly documented large‑load processes, making planning difficult for developers.

Source Type

Industry report / reliability analysis

Confidence Level

High

Notes

Uncertainty rather than a single technical barrier is repeatedly cited as the primary frustration.

Question

40. What causes the biggest delays when trying to get a facility connected?

Extracted Answer

The most frequently cited delay drivers are engineering studies, transmission upgrade construction, and equipment lead times. If studies determine that network upgrades such as new substations or transmission lines are needed, those upgrades can take years to permit and construct. Transformer procurement and other high‑voltage equipment lead times also significantly extend project timelines.

Source

GridLab (2025) Large Loads Interim Report

Nicholas Institute at Duke University (2025) Large Load Interconnection Policy Analysis

DOE Grid Deployment Office publications on transmission build timelines

Evidence or Key Passage

• GridLab notes that transmission infrastructure can take up to a decade to plan, permit, and construct.

• Duke Nicholas Institute reports that utilities have seen multi‑year backlogs when trying to connect large data centers.

Source Type

Industry report / government policy analysis

Confidence Level

High

Notes

Transmission construction timelines often dominate the schedule even when the facility itself can be built in less than two years.

Question

41. Are there parts of the process that feel unnecessary or overly complicated?

Extracted Answer

Some reports indicate that overlapping regulatory and utility requirements can make the process complex. Large load developers often must provide extensive technical data and go through multiple rounds of studies as assumptions change or other projects enter the queue. Stakeholders frequently argue that the process was originally designed for generation interconnections and is still adapting to large loads such as data centers.

Source

Brattle Group & Berkeley Lab (2025) Large Loads: Interconnection, Tariff Designs, and State Actions

GridLab (2025) Large Loads Interim Report

Evidence or Key Passage

• Brattle/Berkeley Lab state that large load interconnection rules are often adapted from generation processes and may not be optimized for load projects.

• GridLab describes situations where ad‑hoc processes and lack of standardization create complexity.

Source Type

Industry research report

Confidence Level

Medium

Notes

Complexity often arises from adapting generation‑oriented processes to load interconnections.

Question

42. Do you feel the process has kept up with the rapid growth of data center demand?

Extracted Answer

Most recent analyses conclude that grid planning and interconnection processes have not fully kept pace with the rapid expansion of hyperscale data centers. The surge in AI‑driven computing demand has created unprecedented load growth in some regions, forcing utilities and regulators to develop new policies and procedures specifically for large loads.

Source

NERC (2025) Reliability Guideline: Risk Mitigation for Emerging Large Loads

DOE reports on data center electricity demand growth

GridLab (2025) Large Loads Interim Report

Evidence or Key Passage

• NERC warns that emerging large loads such as data centers present new operational and planning challenges for the grid.

• Industry reports note that demand growth from AI data centers is accelerating faster than grid infrastructure planning cycles.

Source Type

Reliability guideline / government analysis

Confidence Level

High

Notes

Rapid AI and hyperscale development is widely cited as a major driver of new large‑load policies.

Question

43. Have long interconnection timelines ever forced companies to consider alternative power options such as on-site generation?

Extracted Answer

Yes. Multiple studies indicate that long interconnection timelines are leading some developers to evaluate alternatives such as on‑site generation, co‑located generation, or flexible load arrangements. These strategies can help projects proceed when firm grid capacity is not immediately available.

Source

GridLab (2025) Large Loads Interim Report

DOE and industry analyses of data center power strategies

Evidence or Key Passage

• GridLab notes that developers sometimes pursue co‑located generation or flexible operating arrangements to address interconnection constraints.

Source Type

Industry report

Confidence Level

Medium

Notes

Alternative solutions may include on‑site generation, demand response participation, or phased energization.

Question

44. How often do projects consider building their own power solutions because the grid cannot connect them quickly enough?

Extracted Answer

Industry commentary suggests that the frequency of this consideration is increasing, particularly for hyperscale data centers and AI computing campuses. While not all projects ultimately build private generation, developers increasingly evaluate solutions such as dedicated renewable plants, gas generation, or microgrids to ensure reliable power when grid timelines are uncertain.

Source

NERC (2025) Emerging Large Load Reliability Guidance

GridLab (2025) Large Loads Interim Report

Energy industry news coverage of hyperscale data center power strategies

Evidence or Key Passage

• NERC highlights that large loads may pursue alternative solutions or operational arrangements to mitigate reliability risks.

• Industry reporting notes rising interest in co‑located generation and private power supply for hyperscale data centers.

Source Type

Industry analysis / reliability guidance

Confidence Level

Medium

Notes

Interest in self‑supplied power is rising but varies widely depending on region and project scale.